## Master-Detail
DỰ ÁN GTN | [5 empty] | Update: | 24/7/2015 |  |  | Creator: | XuanDT
[6 empty] | Total | Done ○ | In progress △,▲,★ | Not start ◇ | Start Over ▲ | Finish Over ★ | [132 empty] | Date： 02/07/2018
[6 empty] | 68 | 68 | 0 | 0 | 0 | 0
Summary Information
[7 empty] | 2015-07-06 | 2015-07-31 | 2015-07-06 | 2015-07-24 |  | 2015 | 0 |  | 0 |  | 6 | [126 empty] | Note
No | Lv | Category | Screen | Working | Note/Link | PG | Plan |  | Actual |  | Progress |  | Cost Plan |  | Cost Actual | time axis 2015-06-27 to 2015-10-31
[7 empty] | Start | Finish | Start | Finish |  |  | Hours | Days | Hours | Days | 42182 | 42183 | 42184 | 42185 | 42186 | 42187 | 42188 | 42189 | 42190 | 42191 | 42192 | 42193 | 42194 | 42195 | 42196 | 42197 | 42198 | 42199 | 42200 | 42201 | 42202 | 42203 | 42204 | 42205 | 42206 | 42207 | 42208 | 42209 | 42210 | 42211 | 42212 | 42213 | 42214 | 42215 | 42216 | 42217 | 42218 | 42219 | 42220 | 42221 | 42222 | 42223 | 42224 | 42225 | 42226 | 42227 | 42228 | 42229 | 42230 | 42231 | 42232 | 42233 | 42234 | 42235 | 42236 | 42237 | 42238 | 42239 | 42240 | 42241 | 42242 | 42243 | 42244 | 42245 | 42246 | 42247 | 42248 | 42249 | 42250 | 42251 | 42252 | 42253 | 42254 | 42255 | 42256 | 42257 | 42258 | 42259 | 42260 | 42261 | 42262 | 42263 | 42264 | 42265 | 42266 | 42267 | 42268 | 42269 | 42270 | 42271 | 42272 | 42273 | 42274 | 42275 | 42276 | 42277 | 42278 | 42279 | 42280 | 42281 | 42282 | 42283 | 42284 | 42285 | 42286 | 42287 | 42288 | 42289 | 42290 | 42291 | 42292 | 42293 | 42294 | 42295 | 42296 | 42297 | 42298 | 42299 | 42300 | 42301 | 42302 | 42303 | 42304 | 42305 | 42306 | 42307 | 42308
1
2
3 | 1 | WebBusiness | 01_Trang chủ chưa đăng nhập | Design |  | TuyenTV | 2015-07-06 | 2015-07-31 | 2015-07-06 | 2015-07-24 | 100 | ○
4 |  |  | 02_Giới thiệu | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
5 |  |  | 03_Dịch vụ | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
6 |  |  | 04_Chính sách sử dụng | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
7 |  |  | 05_Bảng giá | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
8 |  |  | 06_Kết quả tìm kiếm theo vận đơn | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
9 |  |  | 07_Tinh cước phí | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
10 |  |  | 08_Tuyển dụng vs Tin tức danh sách | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
11 |  |  | 09_Tuyển dụng vs Tin tức chi tiết | Design |  | TuyenTV | 2015-07-09 | 2015-07-31 | 2015-07-10 | 2015-07-24 | 100 | ○
12 |  | WebCustomer | 01_Đăng nhập | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
13 |  |  | 02_Đăng ký | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
14 |  |  | 03_Đăng ký thành công | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
15 |  |  | 03_Quên mật khẩu | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
16 |  |  | 04_Trang chủ sau khi đăng nhập | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
17 |  |  | 06_Thông tin cơ bản khách hàng | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
18 |  |  | 07_Thay đổi mật khẩu | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
19 |  |  | 08_Quản lý địa chỉ kho hàng | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
20 |  |  | 08_Thay đổi mật khẩu | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
21 |  |  | 09_Thêm mới địa chỉ kho hàng | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
22 |  |  | 10_Cập nhật địa chỉ kho hàng | Design |  | TuyenTV | 2015-07-12 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
23 |  |  | 11_Quản lý tài khoản ngân hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
24 |  |  | 12_Thêm mới tài khoản ngân hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
25 |  |  | 13_Cập nhật tài khoản ngân hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
26 |  |  | 14_Thiết lập thông báo | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
27 |  |  | 15_Tổng quan đơn hàng (Đơn hàng theo trạng thái) | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
28 |  |  | 16_Tìm kiếm đơn hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
29 |  |  | 17_Tạo 1 đơn hàng nhanh | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
30 |  |  | 18_Tạo nhiều đơn hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
31 |  |  | 19_Import Đơn hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
32 |  |  | 20_Import Đơn hàng_Confirm | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
33 |  |  | 21_Cập nhật thông tin đơn hàng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
34 |  |  | 22_Quản lý các phiên chuyển tiền | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
35 |  |  | 23_Quản lý các phiên chuyển tiền chi tiết | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
36 |  |  | 24_Bảng giá_Tính cước phí | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
37 |  |  | 25_Chính sách sử dụng | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
38 |  |  | 26_Hướng dẫn | Design |  | TuyenTV | 2015-07-15 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
39 |  | WebManager | 01_Login | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
40 |  |  | 02_Trang chủ hệ thống | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
41 |  |  | 03_Province_Quản trị tỉnh thành phố | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
42 |  |  | 04_Province_Thêm mới tỉnh, thành phố | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
43 |  |  | 05_Province_Cập nhật tỉnh, thành phố | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
44 |  |  | 06_Branch_Quản lý chi nhánh Kho | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
45 |  |  | 07_Branch_Thêm mới chi nhánh Kho | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
46 |  |  | 08_Branch_Cập nhật thông tin chi nhánh Kho | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
47 |  |  | 09_Area_Quản lý khu vực_Quận_Huyện | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
48 |  |  | 10_Area_Thêm mới khu vực_Quận_Huyện | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
49 |  |  | 11_Area_Cập nhật khu vực_Quận_Huyện | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
50 |  |  | 12_Tin tức_Danh mục tin tức | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
51 |  |  | 13_Tin tức_Thêm mới tin tức | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
52 |  |  | 14_Tin tức_Cập nhật tin tức | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
53 |  |  | 15_Nhân viên_Quản trị nhân viên | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
54 |  |  | 16_Nhân viên_Thêm mới nhân viên | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
55 |  |  | 17_Nhân viên_Cập nhật thông tin nhân viên | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
56 |  |  | 18_Nhân viên_Thay đổi mật khẩu | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
57 |  |  | 19_Khách hàng_Quản trị khách hàng | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
58 |  |  | 20_Đơn hàng_Tìm kiếm đơn hàng | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
59 |  |  | 21_Đơn hàng_Cập nhật thông tin đơn hàng | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
60 |  |  | 22_Đơn hàng_Chuyển ngược trạng thái đơn hàng | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
61 |  |  | 23_Chuyến đi_Tìm kiếm chuyến đi | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
62 |  |  | 24_Chuyến đi_Tạo chuyến đi | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
63 |  |  | 25_Chuyến đi_In biên bản chuyến đi | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
64 |  |  | 26_Chuyến đi_Thêm và Kết thúc chuyến đi | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
65 |  |  | 27_Phiếu thu_Quản lý + Tìm kiếm phiếu thu | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
66 |  |  | 28_Phiếu thu_Chi tiết vs Cập nhật phiếu thu | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
67 |  |  | 29_Phiên chuyển tiền_Tìm kiếm phiên chuyển tiền | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
68 |  |  | 30_Phiên chuyển tiền_Tạo phiên chuyển tiền | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
69 |  |  | 31_Phiên chuyển tiền_Cập nhật phiên chuyển tiền | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
70 |  |  | 32_Báo cáo Thống kê | Design |  | TuyenTV | 2015-07-11 | 2015-07-31 | 2015-07-11 | 2015-07-24 | 100 | ○
71
72
Note on S9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2015-02-16 | Nghỉ tết
2 | 2015-02-17 | Nghỉ tết | 8 | Plan | 8 | Actual | 30 | Current Date
3 | 2015-02-18 | Nghỉ tết
4 | 2015-02-19 | Nghỉ tết |  | 0-99% |  | 100% |  | Saturday
5 | 2015-02-20 | Nghỉ tết
6 |  |  | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7
8 |  |  | ★ | finish over | ○ | Done
9
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## use_guide
○ | cong viec da hoan thanh 100%
★ | cong viec da bi over deadline
△ | Cong viec dang thuc hien (dung nhu plan)
◇ | cong viec chua start